## Checklist
Roofing Project Management Checklist
One checklist per job. Walk each gate in order. Don't pass a gate until its checks are done.
Shaded cells are for you to fill in. In the Done column, use the dropdown to tick an item off.
JOB DETAILS
Job name / number: |  | Site address:
Estimator: |  | Project manager:
Start date: |  | Target completion:
GATE 1: ESTIMATING
Margin is set here. Whatever gets priced in is the ceiling on what the job can return.
Done | Check | Owner | Date | Notes / deficiencies
Roof measured off the plans, with takeoff quantities recorded (not hand-counted or eyeballed).
Every takeoff line priced against current dealer pricing, dated to confirm it's not last job's numbers.
Estimate built from the saved roofing template (tear-off, underlayment, flashing, disposal all present).
Finished bid reviewed line by line for missing items, and signed off before it's sent.
GATE 2: SCHEDULE & WEATHER
A schedule only holds if it survives a change, and on a roof something always changes.
Done | Check | Owner | Date | Notes / deficiencies
Task list entered in sequence (tear-off, dry-in, install, flashing, cleanup), each with a duration and a dependency.
A crew and materials assigned to every task, checked for no double-booking.
One shared schedule published to both field and office (no separate office version or text thread).
Schedule built from or linked to the estimate, confirmed to match the priced scope.
Weather forecast pulled and logged for the tear-off and dry-in days before the crew is dispatched.
Go / no-go weather call recorded for each weather-exposed day before the crew rolls out.
GATE 3: MATERIAL ORDERING
An order that doesn't match the takeoff becomes reorders, delays, and overruns.
Done | Check | Owner | Date | Notes / deficiencies
Order generated from the estimate's priced line items (not rebuilt as a separate list).
Order quantities checked against the takeoff before it's placed.
Order priced against current local rates at time of ordering.
Delivered invoice reconciled against the order (quantity and price) before it's paid.
GATE 4: COST TRACKING
Without a live view of actual against budget, there's no signal to act while there's still time.
Done | Check | Owner | Date | Notes / deficiencies
Committed cost and actual cost set up as two tracked categories at job creation.
A recurring actual-vs-estimate check scheduled on the job (a milestone or a set number of days).
Every change order logged against the job, with cost and scope, before that work proceeds.
GATE 5: FINAL INSPECTION
A failed inspection or messy handover delays final payment and costs you the referral.
Done | Check | Owner | Date | Notes / deficiencies
Fall-protection and safety documentation completed for the job against the OSHA fall-protection standard.
Site walked before the client walkthrough, checked against the I-Codes, defects photographed.
Punch list logged in the standard format (description, location, photo, owner, completion date on each item).
Every punch list item verified resolved and marked closed.
Final walkthrough completed with the prime contractor and sign-off collected.
Final payment processed.