## Instructions
Construction Quality Control Plan Template
A stage-by-stage inspection plan you can adapt to your next job.
How to use this template
This template turns the components of a quality control plan into a working checklist. Each row is an inspection checkpoint tied to a stage of the build. Work down the list as the job progresses, filling in what you checked, what it was measured against, and whether it passed before the next stage covers it up.
Filling in each column
Build stage — The phase of work being inspected. Stages are pre-filled for a typical residential build. Add, remove, or rename rows to match your scope.
What's being checked — The specific item at that stage, not just the stage name. "Rebar size and spacing," not "foundation."
Standard / spec reference — What the work is measured against: the contract spec, a building code section, or the manufacturer's install instructions.
Hold point? — Mark "Yes" for checkpoints where work must stop until it is signed off, because the next stage will cover it. Pre-pour, rough-in before drywall, and waterproofing are the usual ones.
Inspector — Who is responsible for checking this item and has the authority to sign it off.
Result (Pass / Fail) — The clear outcome for this checkpoint. Keep it to Pass or Fail so it isn't left to interpretation later.
Date checked — When the inspection took place.
Notes / deficiencies — Anything that failed and what's needed to correct it. This is your record if a question comes up later.
Re-check date / sign-off — When a failed item was corrected and verified. A checkpoint isn't closed until this is filled in.
A few things to keep in mind
• The yellow cells on the QC Plan tab are the ones you fill in.
• Local government inspections check minimum code, not your standard of quality. This plan is your own walk-through on top of that.
• The earlier a defect is caught, the cheaper it is to fix. Hold points exist so nothing gets buried before it's verified.
• Keep it lightweight. A plan the crew actually uses beats a long one nobody opens.

## QC Plan
Construction Quality Control Plan
Project: |  |  |  | Builder / company:
Fill in the yellow cells. Rows below are a starting point for a typical residential build — adapt them to your scope. Row 5 is a filled-in example.
Build stage | What's being checked | Standard / spec reference | Hold point? | Inspector | Result (Pass / Fail) | Date checked | Notes / deficiencies | Re-check date / sign-off
Foundation (example) | Rebar size, spacing, and cover before pour | Structural drawings S-2; ACI 318; local code | Yes | Site supervisor | Pass | MM/DD/YYYY | Corner bar spacing corrected to 12" o.c. before pour | MM/DD/YYYY — verified
Site prep / excavation | Setout, bench levels, excavation depth, soil bearing | Site plan; geotech report; local code | No
Footings / foundation | Rebar size and spacing, formwork, embeds before pour | Structural drawings; ACI 318; local code | Yes
Slab / foundation pour | Concrete mix, placement, finish, curing | Structural spec; supplier mix design | Yes
Framing | Member size, spacing, connections, alignment, bracing | Structural drawings; local code | Yes
Roof structure / covering | Trusses, sheathing, underlayment, flashing | Manufacturer instructions; local code | No
Waterproofing / weatherproofing | Membrane continuity, flashing, terminations | Manufacturer instructions; local code | Yes
Rough-in: plumbing | Pipe routing, supports, pressure test, penetrations | Plumbing code; plans | Yes
Rough-in: electrical | Conduit, wiring, box placement, penetrations | Electrical code; plans | Yes
Rough-in: HVAC | Duct runs, supports, sealing, penetrations | Mechanical code; plans | Yes
Insulation | Type, coverage, R-value, gaps and voids | Energy code; spec | Yes
Drywall | Fastening, joints, moisture areas, finish level | Spec; manufacturer instructions | No
Exterior finishes | Cladding, trim, sealing, paint prep | Spec; manufacturer instructions | No
Interior finishes | Cabinetry, flooring, trim, paint, fixtures | Spec; client selections | No
Final walkthrough / punch list | Full home review against contract and selections | Contract; client selections; local code | No