## Instructions
Construction Schedule Template
How to use this template
1. Fill in the job header on the Schedule tab (job name, client, start date, prepared by).
2. Durations are typical for a 2,000 sq ft custom residential build. Adjust for lot conditions, crew size, and local factors.
3. Start Day and End Day are business days from project start. Replace with calendar dates once your real start date is set.
4. The Depends On column shows the primary predecessor task that must finish first.
5. Weekly Gantt bars on the right of the schedule shift automatically when you change Start Day or Duration.
6. Add rows within a phase for trade-specific tasks. Delete rows that do not apply to the job.
7. For remodel projects, delete the Site Prep and Foundation phases and begin with a Demolition phase.
8. Update the Status column as work progresses: Not Started, In Progress, Delayed, Complete.
Phase color legend
Site Prep
Foundation
Framing and Dry-In
MEP Rough-Ins
Insulation and Drywall
Finishes
Final Inspections
Punch List and Closeout
Notes
• Total planned duration in this template: 111 business days (roughly 5.5 months at a 5-day work week).
• Add 15 to 20 percent contingency to weather-exposed and inspection-dependent phases.
• Weekly Gantt bars on the Schedule tab are for at-a-glance status. For day-level detail, insert additional columns.
• Print the Schedule tab to PDF for job-site posting or for handoff to subs who are not on the software.

## Schedule
CONSTRUCTION SCHEDULE
Job name: |  | [enter job name]
Client: |  | [enter client name]
Job address: |  | [enter site address]
Start date: |  | [enter start date]
Estimated completion: |  | [enter target date]
Prepared by: |  | [enter preparer name]
Last updated: |  | [enter date]
# | Phase | Task | Duration (days) | Start Day | End Day | Depends On | Assigned Crew | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
1 | Site Prep | Site clearing and grubbing | 2 | 1 | 2 |  | GC crew | Not Started
2 | Site Prep | Rough grading | 1 | 3 | 3 | 1 | Excavator sub | Not Started
3 | Site Prep | Temporary utilities and site signage | 1 | 3 | 3 | 1 | GC crew | Not Started
4 | Site Prep | Erosion control installation | 1 | 4 | 4 | 2 | GC crew | Not Started
5 | Site Prep | Foundation layout and staking | 1 | 5 | 5 | 4 | Framing sub | Not Started
6 | Foundation | Excavation for footings | 2 | 6 | 7 | 5 | Excavator sub | Not Started
7 | Foundation | Footings formwork and rebar | 2 | 8 | 9 | 6 | Concrete sub | Not Started
8 | Foundation | Footings inspection | 1 | 10 | 10 | 7 | Inspector | Not Started
9 | Foundation | Footings pour and cure | 3 | 11 | 13 | 8 | Concrete sub | Not Started
10 | Foundation | Foundation walls formwork and rebar | 3 | 14 | 16 | 9 | Concrete sub | Not Started
11 | Foundation | Foundation walls pour | 1 | 17 | 17 | 10 | Concrete sub | Not Started
12 | Foundation | Foundation cure | 7 | 18 | 24 | 11 | — | Not Started
13 | Foundation | Foundation waterproofing | 1 | 25 | 25 | 12 | Waterproofing sub | Not Started
14 | Foundation | Backfill and rough grade | 2 | 26 | 27 | 13 | Excavator sub | Not Started
15 | Foundation | Basement slab or crawlspace prep and pour | 2 | 28 | 29 | 14 | Concrete sub | Not Started
16 | Framing and Dry-In | First floor deck framing | 2 | 30 | 31 | 15 | Framing sub | Not Started
17 | Framing and Dry-In | First floor wall framing | 3 | 32 | 34 | 16 | Framing sub | Not Started
18 | Framing and Dry-In | Second floor deck framing | 2 | 35 | 36 | 17 | Framing sub | Not Started
19 | Framing and Dry-In | Second floor wall framing | 3 | 37 | 39 | 18 | Framing sub | Not Started
20 | Framing and Dry-In | Roof framing (trusses or rafters) | 3 | 40 | 42 | 19 | Framing sub | Not Started
21 | Framing and Dry-In | Roof sheathing | 1 | 43 | 43 | 20 | Framing sub | Not Started
22 | Framing and Dry-In | Roofing dry-in (underlayment) | 1 | 44 | 44 | 21 | Roofing sub | Not Started
23 | Framing and Dry-In | Exterior wall sheathing and house wrap | 2 | 45 | 46 | 22 | Framing sub | Not Started
24 | Framing and Dry-In | Windows and exterior doors installation | 2 | 47 | 48 | 23 | Framing sub | Not Started
25 | Framing and Dry-In | Roofing final (shingles or metal) | 3 | 45 | 47 | 22 | Roofing sub | Not Started
26 | Framing and Dry-In | Framing inspection | 1 | 49 | 49 | 24 | Inspector | Not Started
27 | MEP Rough-Ins | Rough plumbing | 4 | 50 | 53 | 26 | Plumber | Not Started
28 | MEP Rough-Ins | Rough HVAC | 4 | 50 | 53 | 26 | HVAC sub | Not Started
29 | MEP Rough-Ins | Rough electrical | 5 | 54 | 58 | 27 | Electrician | Not Started
30 | MEP Rough-Ins | Low-voltage rough (data, security, AV) | 2 | 54 | 55 | 26 | Low-voltage sub | Not Started
31 | MEP Rough-Ins | Plumbing inspection | 1 | 59 | 59 | 27 | Inspector | Not Started
32 | MEP Rough-Ins | HVAC inspection | 1 | 59 | 59 | 28 | Inspector | Not Started
33 | MEP Rough-Ins | Electrical inspection | 1 | 59 | 59 | 29 | Inspector | Not Started
34 | Insulation and Drywall | Insulation installation | 2 | 60 | 61 | 32 | Insulation sub | Not Started
35 | Insulation and Drywall | Insulation inspection | 1 | 62 | 62 | 34 | Inspector | Not Started
36 | Insulation and Drywall | Drywall hanging | 3 | 63 | 65 | 35 | Drywall sub | Not Started
37 | Insulation and Drywall | Drywall finishing (tape, mud, sand) | 5 | 66 | 70 | 36 | Drywall sub | Not Started
38 | Insulation and Drywall | Prime coat | 1 | 71 | 71 | 37 | Painter | Not Started
39 | Finishes | Interior painting (first coat) | 3 | 72 | 74 | 38 | Painter | Not Started
40 | Finishes | Cabinetry installation | 4 | 75 | 78 | 39 | Cabinet sub | Not Started
41 | Finishes | Countertop template and fabrication | 5 | 79 | 83 | 40 | Countertop sub | Not Started
42 | Finishes | Tile work (bathrooms and backsplash) | 5 | 79 | 83 | 40 | Tile sub | Not Started
43 | Finishes | Countertop installation | 1 | 84 | 84 | 41 | Countertop sub | Not Started
44 | Finishes | Hardwood flooring installation | 4 | 85 | 88 | 43 | Flooring sub | Not Started
45 | Finishes | Interior trim (base, casing, doors) | 4 | 89 | 92 | 44 | Trim carpenter | Not Started
46 | Finishes | Interior doors hung | 2 | 93 | 94 | 45 | Trim carpenter | Not Started
47 | Finishes | Carpet installation | 2 | 95 | 96 | 46 | Flooring sub | Not Started
48 | Finishes | Plumbing fixtures (final set) | 2 | 95 | 96 | 46 | Plumber | Not Started
49 | Finishes | Electrical fixtures and trim (final) | 2 | 95 | 96 | 46 | Electrician | Not Started
50 | Finishes | HVAC trim and system startup | 1 | 97 | 97 | 49 | HVAC sub | Not Started
51 | Finishes | Final paint (touch-up and second coat) | 3 | 98 | 100 | 50 | Painter | Not Started
52 | Finishes | Appliance installation | 1 | 101 | 101 | 51 | GC crew | Not Started
53 | Finishes | Exterior siding | 5 | 45 | 49 | 23 | Siding sub | Not Started
54 | Finishes | Exterior painting and trim | 4 | 98 | 101 | 53 | Painter | Not Started
55 | Finishes | Driveway and walkway | 3 | 98 | 100 | 51 | Concrete sub | Not Started
56 | Finishes | Landscaping (basic) | 3 | 101 | 103 | 55 | Landscaper | Not Started
57 | Final Inspections | Final plumbing inspection | 1 | 104 | 104 | 52 | Inspector | Not Started
58 | Final Inspections | Final electrical inspection | 1 | 104 | 104 | 52 | Inspector | Not Started
59 | Final Inspections | Final HVAC inspection | 1 | 104 | 104 | 52 | Inspector | Not Started
60 | Final Inspections | Final building inspection and CO | 1 | 105 | 105 | 59 | Inspector | Not Started
61 | Punch List and Closeout | Client walkthrough (pre-punch) | 1 | 106 | 106 | 60 | GC crew | Not Started
62 | Punch List and Closeout | Punch list corrections | 3 | 107 | 109 | 61 | GC crew and subs | Not Started
63 | Punch List and Closeout | Final cleaning | 1 | 110 | 110 | 62 | Cleaning sub | Not Started
64 | Punch List and Closeout | Final walkthrough and handover | 1 | 111 | 111 | 63 | GC crew | Not Started